## Sheet1
date | work | Assignment due
2020-11-04 | Determine project theme and data source
11/5-11/7 | Complete proposal | 11/7, 1pm
11/7-11/8/ | Zoom meeting: draw a big picture on how to analysis data
11/9-11/10 | complete final source collection
11/11-11/13 | Zoom meeting: determine detailed devision of labour
11/14-11/15 | clean and tidy data
11/16-11/17 | Zoom meeting: draw a big picture of website design
11/18-11/20 | clean and tidy data
11/21-11/27 | make graphs and data analysis
11/28-12/2 | prepare paper work for report
12/3-12/4 | Complete report | 12/5, 4pm
12/3-12/5 | complete final webpage improvement and screencast | 12/5, 4pm